## COA
GLOBAL MARKET DEVELOPMENT FUND - PROPOSED CHANGE OF ACTIVITY FORM
Company Name:
Agreement File #:
Item (Activity Name) | Description | Original Dates | Original Budget Estimate $ | Actuals $ | Proposed Replacement Item/Activity | Change (New Dates) | New Budget Estimate $ | Variance $ | Notes - reason for replacing original activity and/or any outcome from new Activity

## Sample Form
SAMPLE CHANGE FORM
Item | Description | Dates | Budget estimate | Actuals | Notes
Activity #1 |  |  |  |  | Cancelled – could not schedule meetings
Activity #2 | RealScreen Summit + meetings - Washington, DC | Feb. 1-6, 2009 | 4725 | 5007.49 | Has taken place – good results – continuing development of rePETS.tv with WETA (PBS)
Activity #3 | Digital Hollywood + meetings - New York | Mar. 16-20, 2009 | 4475 | 4490.5 | Has taken place – good results (led to need for Activity #4)
Activity #4 | NYC agency/CheckM8/TiVo meetings | April 27, 2009 | 1025 | $956.74 | Replaces Activity #1 -
|  |  | (not in original application) |  | Came up quickly – schedules changing until last minute - Has taken place resulting in two agreements signed
Activity #5 | WETA / PIJAC meetings | 2009-05-26 | 1190 | TBD | Also Replaces Activity #1 –
|  |  | (not in original application) |  | Meeting scheduled with WETA (PBS) and Pet Industry Joint Advisory Council (content/sponsor discussions)